## Slide 1: School Lunch Program Update- April 2026

## Slide 2: General Information
2 healthy and scratch-made options 5 days a week for the entirety of the school year
Subsidized meal available to all students in the province
  K-8: $4
  9-12: $5
Service providers may continue to sell their usual à la carte items, but these items will not be subsidized
Online ordering and invoicing directly between provider and EECD

## Slide 3: Timeline
Rollout plan mobilized and ready for September
Communicate rollout plan publicly
Work with schools who have identified gaps
Form plan for any required larger projects with provider and district facilities teams
Schools begin subsidized model across province
Support schools who have identified gaps
Problem solve logistics with districts
May
September
Meet with new and incumbent lunch service providers and discuss needs for Fall program launch
Prototype sites and providers to prepare/begin trial run of lunch program
Find solutions for schools who did not receive bids in the RFP
April
Complete any kitchen renovations/projects before August 20th
Work with providers if needed to ensure readiness
Summer

## Slide 4: RFP Outcome
3 new providers were awarded contracts in ASD-W
  Chartwells, CéD'ici, and Ramada
6 schools in ASD-W did not receive any bids (no service provider has been selected yet)
  OEC: Burton Elementary
  FEC: Kingsclear Community School, McAdam Elementary, McAdam High, and Nashwaak Valley
  WEC: Saint Mary’s Academy

## Slide 5: ASD-W Lunch Providers
6 schools (new)
CéD’ici
34 schools (incumbent), 12 (new)
Chartwells
1 school (incumbent)
Gagetown Food & Fermentation
1 school (incumbent)
Geary Home & School
6 schools (incumbent)
Jobs Unlimited
4 schools (new)
Ramada

## Slide 6: Lunch Providers
Many of the district’s cafeterias have out-of-date, residential-style equipment
Providers and district teams will work together to complete any required renovations to kitchens or equipment procurement
District coordinators will also assist new providers with things like:
  kitchen licensing, coordinating with facilities, communications to schools, and more.

## Slide 7: Prototype Sites
Sunbury West (K-8)
  Chartwells, onsite lunch preparation
Objective: To test the most complex real-world conditions before provincial scale-up as well as work with new to the district providers
Centreville Community School (K-8)
  Ramada, delivery to school
Lincoln Elementary School (K-5)
  CéD’ici, delivery to school

## Slide 8: Parent Communication
Proof of Concept schools will receive communication from districts before May.
Communications will go through EECD → ASD-W → Schools → Parents
Prototype schools will receive communication from districts before May.

## Slide 9: Full Subsidy Administration
EECD to distribute a communication plan that will go to Districts, schools, and families and templates of letters will be shared.
School staff will identify students eligible for full subsidy
EECD to distribute a communication plan that will go to Districts, schools, and families and templates of letters will be shared.

## Slide 10
Online Ordering
Service providers can plan ahead
Stigma reduction and anonymity
Easier tracking and invoicing
Reduced administrative burden

## Slide 11: How will We Measure the Success of the Program?
  Adherence to policy 711 through audits
  Student participation and anonymity
  Providers ability to meet needs of school
  Parent/student/school surveys
  Reductions in food insecurity and absenteeism
  Maintenance of high food quality and food safety practices through audits

## Slide 12: Questions
Mariah Williams: mariah.williams@nbed.nb.ca
Elyse Czapalay: elyse.czapalay@nbed.nb.ca
Notes: Thank you!